## SCOPE

Objectives

There’s about roughly 8 projects that will require varying levels of audio work, we plan on assisting each one by providing tailored audio services. Each of us brings a different area of interest: Riley has shown interest in handling the location sound for a film project, Cody has expressed interest for the post production and sound design, and I’m interested in the sound design, scoring, and overall audio for the game projects. Although each of us will have our primary responsibilities, we’ll be collaborating across all of the projects, just each of us will be the main point of contact for those projects.

Another key objective is to develop communication, strategies and workflows that would reflect real-world practices. As aspiring audio practitioners, we realise that our role often relies on collaboration to help support projects. With current technology, we can make collaborating with other creatives easier (Olatabusan, 2025). To meet this objective, we’ve devised several processes and workflows, these are:

- Project Management Tools: Such as Trello to track projects.

- Centralised Documentation: For all team documentation and project resources.

- Collaborative Team Meeting/Feedback Sessions: Conducted outside class for feedback and workload balance (meeting minutes to be recorded).

- Project Audio Questionnaire: To identify project leads expectations and vision.

- Streamlined Feedback Process: Such as Google Forms/Docs to reduce miscommunication.

- OMF Audio Handover Tutorial Document (Post Production): A tutorial to pass on to the video editor once picture lock is finalised to ensure the project files are exported correctly.

We’ve also developed contingencies, these include:

- Pooled Equipment & Network List: A contact list of peers and audio connection’s equipment to borrow.

- Equipment Hire List: With pricing details.

And our final objective is to have a diverse range of projects for our portfolios. While focusing on one major project has its benefits, showcasing a range of collaborative work leads to a strong portfolio and increases employability.

Key Deliverables

Our deliverables include a presentation and an accompanying portfolio showcasing our contributions to each capstone project we worked on. All DAW project sessions will be included in a shared google drive folder with related audio assets and workflow documentation such as briefs, drafts and revisions.

Team Responsibilities

As a collective agency, we’ve opted to share responsibilities rather than assigning them to each member. There are 3 key roles/responsibilities that each of us will share, the meeting lead (project tracker), who tracks project progress and organises meetings. The meeting scribe, who records the meeting minutes, and the drive and asset organiser. They’re responsible for managing and   the shared documents, assets and resources. These roles are to be rotated between the three of us every week to ensure a balanced and fair workload.

Preliminary Timeline

At the moment, we’ve only received a rough timeline from Harry’s group, so expect this timeline to change as we wait to confirm the other projects. Our draft timeline is as follows’:

TRIMESTER 1

- Week 6: Pitch & Finalisation of Project Workflows.

We’re hoping to finalise half of the project workflows, establish project tools, complete the final draft of the audio questionnaire for review, and the shared Google drive setup.

- Week 7: Project Outreach & Finalisation of Remaining Workflows.

We will be actively reaching out to other capstone leads to lock in, completing the remainder of the workflows, and commencing the equipment lists.

- Week 8-12: Project Pre-Planning.

This is the beginning of the pre-planning phase - we’ll be gathering resources and learning material, creating DAW templates, and asset and equipment lists.

STUDENT BREAK

- Week 1-3: Location Sound For Film

We’re on-call to assist with location sound for the filming of The Blood We Swim In.

TRIMESTER 2

- Week 1-2: Project Work Commences

Any project work that has yet to be started, will commence at this point. Post production for The Blood We Swim In may start depending on when picture lock is complete and we will have 6 weeks to complete and handover the files.

Q

- Week 3-5: Project Feedback

The first round of feedback from the project leads will be happening during this time. Workload checks amongst ourselves, foley, and ADR sessions will be completed by this point. Progress on the dialogue edit and sound design.

- Week 6-8: Film Post Production Finishes & Project Feedback

The final mix for the film post production should be completed. Film project’s lead feedback required before handover.

- Week 9: Portfolio & Presentation/Deliverables Commence With Project Feedback

Preparation for our portfolio and presentation will commence and will be aiming to have 70%+ completion of the remaining projects by this checkpoint.

- Week 10-11: All Project Work Complete

All projects should be completed with all assets finalised and ready for handover.

- Week 12: Present Deliverables & Portfolio

Present our presentation and portfolio with deliverables to accompany.

O. Olatubosun. (2025, February 17). Monetizing Your Creativity: How to Earn a Living from Your Passion. SIRYUS HUB; Siryus Hub. https://www.siryushub.com/collaboration-in-creative-industries